## Sheet1
2025-26 NABIP-TX Strategic Plan
Mission Statement: |  |  |  | 2025-09-30
The mission of the National Association of Benefits and Insurance Professionals, Texas Chapter is to inform and protect the consumer by enhancing the professional growth of its members. |  |  |  | 2025-12-31
2026-03-31
Vision Statement: |  |  |  | 2026-06-30
To protect the future of consumer healthcare financing through education and advocacy while maintaining the highest standards of Ethics and Integrity.
Chair | Goal | Steps To Achieve Goal |  | Due Date | Complete? | NOTES
EC Immed Past Pres | Texas Honorees Corporation (vote this name change in) | Emphasize importance of all opportunities for contributions at BOD meetings | 1st Q | 2025-09-30
|  | conference calls and NABIP-TX Events | 2nd Q | 2025-12-31
|  |  | 3rd Q | 2026-03-31
|  |  | 4th Q | 2026-06-30
| Continue Governance committee to review Bylaws and P&Ps | Monitor all NABIP-TX P&P's/Sunset review and ensure they are current and up to date | 1st Q | 2025-09-30
|  |  | 2nd Q | 2025-12-31
|  |  | 3rd Q | 2026-03-31
|  |  | 4th Q | 2026-06-30
| Approve Bylaws | Bring revised back to board and have membership meeting to approve | 1st Q | 2025-09-30
| Promote LPRT program and achieve blue ribbon status & Gold Certication | Educate the chapters on the program by promoting through blast emails and | 1st Q | 2025-09-30
|  | working with them in gathering information necessary to achieve blue | 2nd Q | 2025-12-31
|  | ribbon status. | 3rd Q | 2026-03-31
|  |  | 4th Q | 2026-06-30
EC Secretary
Membership | Maintain positive growth each quarter and increase retention |  | 1st Q | 2025-09-30
Growth |  |  | 2nd Q | 2025-12-31
|  |  | 3rd Q | 2026-03-31
|  |  | 4th Q | 2026-06-30
| Increase Awareness and Share Best Practices | Monthly chapter calls with Chapter Presidents, Membership/Retention Chairs | 1st Q | 2025-09-30
|  |  | 2nd Q | 2025-12-31
|  |  | 3rd Q | 2026-03-31
|  |  | 4th Q | 2026-06-30
|  | Provide NABIP membership powerpoint presentation for local chapters to use | 1st Q | 2025-09-30
during luncheons and events
|  | Distribute prospective new member packet (NABIP Packet) | 2nd Q | 2025-12-31
| Monthly Outreach | Monthly Chapter eMail with Membership Results/Updates/Reminders | 1st Q | 2025-09-30
|  |  | 2nd Q | 2025-12-31
|  |  | 3rd Q | 2026-03-31
|  |  | 4th Q | 2026-06-30
| Membership Recruitment-Landmark Award | Hold a membership blitz | 1st Q | 2025-09-30
|  |  | 2nd Q | 2025-12-31
|  |  | 3rd Q | 2026-03-31
| Membership Campaign-Landmark Award | 100% Board recruitment contest | 1st Q | 2025-09-30
|  |  | 2nd Q | 2025-12-31
|  |  | 3rd Q | 2026-03-31
| Membership Campaign-Landmark Award | Ongoing membership campaign lasting 3-6 months roadshow | 1st Q | 2025-09-30
|  |  | 2nd Q | 2025-12-31
|  |  | 3rd Q | 2026-03-31
| Landmark Award Documentation | Call minutes and attendance template-Send to Awards Chair | 2nd Q | 2025-12-31
Membership | Increase retention rate to 85% |  | 1st Q | 2025-09-30
Retention |  |  | 2nd Q | 2025-12-31
|  |  | 3rd Q | 2026-03-31
|  |  | 4th Q | 2026-06-30
| Equip Membership/Retention Chairs | eCommerce Training | 1st Q | 2025-09-30
|  | Monthly Email Reminders to Local Membership/Retention Chairs to pull | 1st Q | 2025-09-30
|  | the new member report/lapse report/billed not paid | 2nd Q | 2025-12-31
|  |  | 3rd Q | 2026-03-31
|  |  | 4th Q | 2026-06-30
Chapter Liaison | Reach out to Chapter Presidents in advance of EC visits to | Determine if chapters need assistance with marketing efforts and | 1st Q | 2025-09-30
| see how their marketing of the membership meetings is going | membership recruitment to concide with their events | 2nd Q | 2025-12-31
|  |  | 3rd Q | 2026-03-31
|  |  | 4th Q | 2026-06-30
| DEI Marketing piece | translate pieces to spanish for the website | 2nd Q | 2025-12-31
| Value of Membership Education roadshow | Schedule monthly conference calls to discuss issues, hold webinars and CE | 1st Q | 2025-09-30
|  | at luncheons and special events | 2nd Q | 2025-12-31
|  |  | 3rd Q | 2026-03-31
|  |  | 4th Q | 2026-06-30
Medicare Chair
EC Treasurer
Professional | Educate chapter PD chairs on development process in providing dynamic | Prepare and Disbribute Potential Speaker list to all PD Chairs | 1st Q | 2025-09-30
Development | presentations
|  | Schedule initial and monthly PD Calls | 1st Q | 2025-09-30
|  | Meet with PD chairs and develop scheduling plan of action | 1st Q | 2025-09-30
|  | Provide training for Virtual CE sessions for PD Chairs | 1st Q | 2025-09-30
|  |  | 2nd Q | 2025-12-31
| Include in at least 3 news / communications - Certifications, etc. |  | 3rd Q | 2026-03-31
|  |  | 4th Q | 2026-06-30
Awards | Apply for NABIP Awards | Communicate award criteria and timeline with board chairs - Landmark, | 1st Q | 2025-09-30
|  | Presidential Citation, Media Relations, Legislative Excellence, Website | 2nd Q | 2025-12-31
|  |  | 3rd Q | 2026-03-31
| Continue online submissions | Continue process for NABIP-TX chapter submissions | 1st Q | 2025-09-30
| Dropboxes to open at the beginning of the year at Leadership training |  | 3rd Q | 2025-12-31
|  |  | 4th Q | 2026-03-31
| Conduct quarterly meetings with local awards chairs | Quarterly meetings for dropbox training | 1st Q | 2025-09-30
| Deadline for submission of NABIP-TX awards remains February 25 |  | 2nd Q | 2025-12-31
|  |  | 3rd Q | 2026-03-31
|  |  | 4th Q | 2026-06-30
Chapter Certification- Ongoing per chapter (State was submitted in March)
Vanguard | Provide communication and support for chapter goals | provide specific initiatives for chapter levels | 1st Q | 2025-09-30
|  | succession planning | 2nd Q | 2025-12-31
|  |  | 3rd Q | 2026-03-31
|  |  | 4th Q | 2026-06-30
|  | Host a Vanguard event during the year | 1st Q | 2025-09-30
|  |  | 2nd Q | 2025-12-31
|  |  | 3rd Q | 2026-03-31
|  |  | 4th Q | 2026-06-30
|  | work with colleges with insurance/risk management | 1st Q | 2025-09-30
|  |  | 2nd Q | 2025-12-31
|  |  | 3rd Q | 2026-03-31
|  |  | 4th Q | 2026-06-30
LPRT | Promote LPRT | 4 times a year | 1st Q | 2025-09-30
|  |  | 2nd Q | 2025-12-31
|  |  | 3rd Q | 2026-03-31
|  |  | 4th Q | 2026-06-30
EC 2nd VP
Legislation | Keep membership informed on all association, state and | Have a Legislative Day (virtually) focused on industry legislative and | 1st Q | 2025-09-30
| federal legislative activities. | regulatory developments
|  | Proactive communications with respect to major state or federal issues | 1st Q | 2025-09-30
|  |  | 2nd Q | 2025-12-31
|  |  | 3rd Q | 2026-03-31
|  |  | 4th Q | 2026-06-30
|  | Hold Monthly Teleconferences with the Legislative Council | 1st Q | 2025-09-30
|  |  | 2nd Q | 2025-12-31
|  |  | 3rd Q | 2026-03-31
|  |  | 4th Q | 2026-06-30
|  | Hold Monthly Legislative Teleconferences with the Legislative Council and | 1st Q | 2025-09-30
|  | Local Chapter Legislative Chairs and Chapter Representatives | 2nd Q | 2025-12-31
|  |  | 3rd Q | 2026-03-31
|  |  | 4th Q | 2026-06-30
|  | Develop 2 legislative press releases/ OpEd by 4th quarter | 4th Q | 2026-06-30
| Enhance Key Contacts Program | 100% of assignment to targeted legislators | 4th Q | 2026-06-30
| your local chap reps to deliver checks in your area- need to partner with the state to identify those individuals since you know best who is in your area | key contacts day for local chapters- Emphasis on this at Leg activities & events | 1st or 3rd
| Industry Relations | 8 meetings by the 4th quarter | 4th Q | 2026-06-30
|  | 3 industry partner events attended | 4th Q | 2026-06-30
| Increase member participation in NABIP-PAC and NABIP-TX PAC | 100% of State and Local Board participation | 1st Q | 2025-09-30
|  |  | 2nd Q | 2025-12-31
|  |  | 3rd Q | 2026-03-31
|  |  | 4th Q | 2026-06-30
|  | Top 3 NABIP-TX PAC Contributor Recognition | 3rd Q | 2026-03-31
| Legislative Article in NABIP-TX magazine | One per issue of the magazine | 1st Q | 2025-09-30
|  |  | 2nd Q | 2025-12-31
|  |  | 3rd Q | 2026-03-31
|  |  | 4th Q | 2026-06-30
EC 1st VP
Communications | Actively engage with Chapter Representatives for Press Release to local media | Hold quarterly conference calls | 1st Q | 2025-09-30
|  |  | 2nd Q | 2025-12-31
|  |  | 3rd Q | 2026-03-31
|  |  | 4th Q | 2026-06-30
| Actively engage with Chapter Representatives for Op Ed pieces to local media | Hold quarterly conference calls | 1st Q | 2025-09-30
|  |  | 2nd Q | 2025-12-31
|  |  | 3rd Q | 2026-03-31
|  |  | 4th Q | 2026-06-30
| Gather Media contacts from local Media Chairs | Update media contacts | 1st Q | 2025-09-30
| Submit Press Releases for awards purposes to Online Media/Social Media | awards for state board and awards | 1st Q | 2025-09-30
|  |  | 2nd Q | 2025-12-31
|  |  | 3rd Q | 2026-03-31
|  |  | 4th Q | 2026-06-30
| Submit Op Ed Pieces to the Media | op-eds | 1st Q | 2025-09-30
|  |  | 2nd Q | 2025-12-31
|  |  | 3rd Q | 2026-03-31
|  |  | 4th Q | 2026-06-30
| Present Working With The Media presentation at the Strategic Planning Meeting | Present Working With The Media presentation at Leadership Training | 1st Q | 2025-09-30 | 2025-07-16
| Win National Media Award | Send award requirements to Awards Chair as they are received. | 3rd Q | 2026-03-31
NABIP-TX Enews | Keep membership informed of state chapter activities | Distribute Enews monthly to include information regarding chapter 'bragging' & events- due by first of every month | 1st Q | 2025-09-30
| on a regular basis. | Distribute | 2nd Q | 2025-12-31
|  |  | 3rd Q | 2026-03-31
|  |  | 4th Q | 2026-06-30
|  | Update format and look to include Hot links to FB, etc. | 1st Q | 2025-09-30
Magazine | Keep the membership informed on association activities | Have electronic issues published on time each quarter. | 1st Q | 2025-09-30
| with articles to enhance knowledge and member | (Per issue requirements and due dates will be distributed to Chapter | 2nd Q | 2025-12-31
| development. | Presidents and NABIP-TX Board by August 1, 2025) | 3rd Q | 2026-03-31
|  |  | 4th Q | 2026-06-30
Technology | Improve the traffic to the NABIP-TX website and win the NABIP website award | Work with awards chair | 1st Q | 2025-09-30
|  | Provide Spanish translation and other ADA capabilities to site | 2nd Q | 2025-12-31
| Review and update the website |  | 2nd Q | 2025-12-31
| Increase Social Media presence | goal: weekly posts with industry content, photos from meetings, new member highlights, medicare news | 1st Q | 2025-09-30
|  |  | 2nd Q | 2025-12-31
|  |  | 3rd Q | 2026-03-31
|  |  | 4th Q | 2026-06-30
SysOp | Keep communication channels open and current | Update state and chapter board rosters | 1st Q | 2025-07-15
EC President Elect
Convention | Achieve or exceed budgeted attendance and sponsorship goals | Develop an appealing and catchy theme | 1st Q | 2025-09-30
|  | Identify important topics of interests for brokers/members by survey | 1st Q | 2025-09-30
What is their main focus and concerns as well as target population
|  | Save the date in Enews & NABIP-TX Magazine | 1st Q | 2025-12-31
|  | Save the date to potential exhibitors & sponsors that includes an offer to | 1st Q | 2025-09-30
sponsor the same event.
|  | Build agenda with dynamic speakers focused around the needs identified | 1st Q | 2025-09-30
|  | by brokers/members and driving increased attendance | 2nd Q | 2025-12-31
|  | Expand list of exhibitors and sponsors | 1st Q | 2025-09-30
|  | Actively market to exhibitors & sponsors | 2nd Q | 2025-12-31
|  |  | 3rd Q | 2026-03-31
|  |  | 4th Q | 2026-06-30
|  | Engage local chapter's participation and increase marketing emails to each | 2nd Q | 2025-12-31
|  | chapter. | 3rd Q | 2026-03-31
|  |  | 4th Q | 2026-06-30
|  | Actively market to other associations and trade industries - Build List of Contacts | 2nd Q | 2025-12-31
|  |  | 3rd Q | 2026-03-31
|  |  | 4th Q | 2026-06-30
|  | Marketing through social media | 2nd Q | 2025-12-31
|  |  | 3rd Q | 2026-03-31
|  |  | 4th Q | 2026-06-30
|  | Expand list of attendees to include non-members | 1st Q | 2025-09-30
|  | Thank you to Exhibtors/Sponsors - Discuss commitment for next year | 4th Q | 2026-06-30
|  | Host a Welcome reception event at the conference | 4th Q | 2026-06-30
Chapter Presidents | Promote 100% NABIP-TX PAC participation by local board members | Include on every board meeting agenda for discussion | 1st Q | 2025-09-30
|  |  | 2nd Q | 2025-12-31
|  |  | 3rd Q | 2026-03-31
|  |  | 4th Q | 2026-06-30
| Promote 100% NABIP PAC participation by local board members | Include on every board meeting agenda for discussion | 1st Q | 2025-09-30
|  |  | 2nd Q | 2025-12-31
|  |  | 3rd Q | 2026-03-31
|  |  | 4th Q | 2026-06-30
| Promote 100% Convention attendance by local board members | Include on every board meeting agenda for discussion | 1st Q | 2025-09-30
|  |  | 2nd Q | 2025-12-31
|  |  | 3rd Q | 2026-03-31
|  |  | 4th Q | 2026-06-30
| Promote Triple Crown and LPRT |  | 1st Q | 2025-09-30
|  |  | 2nd Q | 2025-12-31
|  |  | 3rd Q | 2026-03-31
|  |  | 4th Q | 2026-06-30
| Increased participation in meetings | find new speakers, new ideas, to help bring in members who aren't currently participating | 1st Q | 2025-09-30
|  | improve community outreach | 2nd Q | 2025-12-31
|  |  | 3rd Q | 2026-03-31
|  |  | 4th Q | 2026-06-30
Attend State Monthly Leg Calls
Attend Annual Leadership Training
Attend State PD Calls
Attend State Membership Calls